## Sheet1
Project Assignment Number: | 2010 | [8 empty] | 2011 |  |  |  | Days | Days | Days
| A | M | J | J | A | S | O | N | D | J | F | M | Who | Richard | Tim | Thong
Project supervision
Review workplan | [12 empty] | Richard / Tim | 3 | 1
Provide and review budgets; allocate budgets. | [12 empty] | Richard | 2
Communications and profiling | [12 empty] | Richard + Tim + IIED | 4 | 2
Liase with IIED. | [12 empty] | Richard | 3
RM for expanding project area to phase 2 | [12 empty] | Richard | 8 | 1
Project establishment
Establish permissions, office in Phu My commune, CT district | [12 empty] | Richard, Hung, Lam | 2 |  | 3
Meet with officials in Bao Lam district to discuss working in Loc Bac commune | [12 empty] | Thong + Tim |  |  | 7
Preliminary field visit and area assessment | [12 empty] | Thong + Tim |  | 7
Finalize project boundaries | [12 empty] | Tim + Thong | 1
Finalize agreement with CIFOR on socio-economic assessments | [12 empty] | Richard + Tim | 1 | 1
Carbon assessment
Preliminary carbon assessment / forest type check | [12 empty] | RCFEE
Adjust maps based on above to improve forest stratification | [12 empty] | RCFEE / STI / TIm |  | 2
Design sampling strategy for full carbon assessment and long-term monitoring | [12 empty] | Tim + RCFEE |  | 3 | 3
Design training materials for community carbon monitoring | [12 empty] | IIED + Tim + Thong +UN? |  | 2 | 2
Socio-economic and biodiversity baselines
Initial description of communities in project area including social, economic, and cultural characteristics | [12 empty] | Thong + Tim |  | 6 | 6
Identify land areas that are fundamental for meeting the basic needs of local communities | [12 empty] | Thong + Tim |  |  | 1
Develop community variables to be monitored and monitoring plan | [12 empty] | Thong + Tim + CIFOR / IIED |  | 4 | 5
Develop description of current biodiversity within the project zone (diversity of species and ecosystems) | [12 empty] | ITB + Tim + Thong |  | 2 | 3
Describe threats to biodiversity | [12 empty] | ITB + Tim |  | 1
Develop indicators and monitoring plan to monitor changes in biodiversity throughout project life | [12 empty] | ITB + Tim |  | 3
Assessment of drivers of deforestation
Manage outputs from Thu Ba | [12 empty] | Tim |  | 2
Further assessment of land tenure status (especially in Loc Bac) | [12 empty] | Thong (CIFOR) + Tim |  | 2 | 5
Further assessment to quantify mobility of drivers | [12 empty] | Thong + Tim + national consultant? (if needed) |  | 3 | 5
Spatial modeling of deforestation
Enquiries: Winrock for cost of training or other groups for doing it as consultancy | [12 empty] | Tim |  | 1
ToR, tendering, managing outputs for spatial modeling consultant | [12 empty] | Tim |  | 4
Spatial modeling using GeoMod (IDRISI) | [12 empty] | Consultant / Tim |  | 0
Government relationship building
Introduce district staff to REDD | [12 empty] | Thong + Tim |  | 3 | 4
Gain support of district for community-focused REDD | [12 empty] | Thong |  |  | 8
Decide best structure for advisory group | [12 empty] | Thong |  |  | 8
Community engagement
Provide best practice guideleins on introducing REDD to communities | [12 empty] | IIED + All | 1 | 1
Informing communities about REDD | [12 empty] | Thong + Tim |  | 5 | 5
Assessment of livelihood options for local communities | [12 empty] | Thong + Tim + national consultant | 1 | 3 | 10
Obtaining consent | [12 empty] | Thong + Tim
Feedback on activities and benefit distribution | [12 empty] | Thong + Tim |  | 8 | 8
Identification of target groups within communities where REDD intervention will be most effective | [12 empty] | Thong + Tim |  |  | 6
Identify interest and groups for carbon monitoring | [12 empty] | Thong + Tim |  |  | 6
Trainings in carbon monitoring | [12 empty] | RCFEE + Tim + Thong |  | 3 | 3
Capacity building in identified livelihood alternatives to reduce deforestation | [12 empty] | Thong + IIED + SNV VCD |  |  | 18
Benefit distribution
Study on international best practices and lessons learned for fund distribution structures (REDD / PES) | [12 empty] | IIED
Identify legal requirements and process for using FPDF | [12 empty] | Suzanne
Assess other potential institutions / structures in VN | [12 empty] | Suzanne
Initiate discussions on using FPDF (or other mech): national | [12 empty] | Richard + Thong + Tim | 2 |  | 5
Discussion on Fund with local groups | [12 empty] | Thong |  |  | 10
Project Design Document (PDD) writing (phase 1 values)
Writing assessment of drivers | [12 empty] | Tim + Thong |  | 2 | 3
Writing assessment of mobility of drivers (leakage) | [12 empty] | Tim + Thong |  | 2 | 3
First draft of PDD with information available at that point | [12 empty] | Tim | 2 | 8
Calculate biomass / carbon relationships | [12 empty] | RCFEE + Tim |  | 2
Complete emissions tables | [12 empty] | Tim + RCFEE |  | 4
Second draft of PDD - complete | [12 empty] | Tim | 2 | 8
Explore options for selling credits | [12 empty] | Richard | 5
[13 empty] | TOTAL | 37 | 96 | 137
Note on P6: Tim Holland: if I'm only at 2 days over the whole year for this, you may have to learn how to make maps ;)
Note on Q10: Thong: I think I should also involve into this task to get familiar with the local authority for easier
Note on P17: Tim Holland: supervision of process and discussion
Note on P19: Tim Holland: This is assuming IIED does the bulk of the work. If me and Thong have to do most of it, this will move up
Note on Q19: Thong: Agree with Tim's comment, I'd also expect to join some activities prior to this task such as short training/coaching on community carbon monitoring...
Note on P24: Tim Holland: This is mainly me doing the ToR etc at the front end, and reviewing their inputs, standardizing for PDD at the back end (same for point below)
Note on Q29: Thong: I just make a rough estimation for this task of 1 commune
Note on P33: Tim Holland: or if I end up doing it, this would go towards that.
Note on P34: Tim Holland: If I do this, it may be a major task. I don't really know what is entailed yet. If I don't do it, may be pricey.
Note on Q36: Thong: given two selected ditricts (Cat Tien and Bao Lam)
Note on Q37: Thong: Throughout the year
Note on Q38: Thong: Throughout the year
Note on Q41: Thong: given three communes selected
Note on Q42: Thong: assuming that a national consultant is mobilised to conduct this task at village level rather than commune level in three selected communes. The below task will also be done at the same time
Note on P44: Tim Holland: This includes the points below that would happen on the same mission
Note on Q44: Thong: same as Tim
Note on N47: Tim Holland: RCFEE on this component could come from LCB budget
Note on N48: Tim Holland: IIED can help us develop some materials.
Note on Q48: Thong: 3days/month/3communes throughout 6 month
Note on P64: Tim Holland: this is a little under, but if I take back the spatial modeling it will go a little over. So depends what we do with that.