## Slide 1: Monitoring and Evaluation Plan
Systematising the collection of evidence

## Slide 2: Developing an M&E Plan
Issues to consider
M&E management
Purpose of the plan
Resource needs HR and £
Timing and sequencing
Feedback and lesson-learning
Provision of sound evidence

## Slide 3: Who Measures What?
Who is responsible
Who needs to be included in the monitoring process
Who needs to be included in the evaluation process
What aspects are you measuring
Milestones
Indicators
Assumptions
Risks
Notes: This is a very important slide and adequate time should be allowed for discussion.
Note the slide presentation is in three parts which correspond to important learning points.
Firstly, the core sequence of Inputs to impact.
Secondly, the internal/external perspective
Thirdly the matching but opposite environmental issues that management control diminishes and external factors become more important as the chain progresses further from inputs to impact.
Core sequence
Show the core sequence and talk through the description of each stage from inputs to impact.
The terms are in wide use in international and national public sector processes and there is wide agreement about their use.
Internal/External
The sequence has two parts to it: those items under the control of management and those that are more dependent on external factors.
The use of inputs, management of activities and delivery of outputs are under management’s direct control. Management of output delivery is handled by processes that are within the organisation.
The success of timely and accurate delivery of outputs is something that managers can be held directly accountable for.
As such, this part of the results chain is considered to be ‘Internal’ to the process and comprises the internal perspective.
Show the Internal Perspective – External Perspective part of the slide
The achievement of outcomes, however, depends on how the people or institutions which are the focus of the activities react to the outputs that are delivered.
Management of progress towards outcomes and impact requires interaction with stakeholders and an understanding of their views about the outputs. That is why it is considered to be an external perspective.
This is not under the direct control of management, but, given that the reaction will depend on the quality and appropriateness of the outputs, it is said that managers can be held accountable for managing towards outcomes.
Impact is a long-term aim. Impact will usually depend not on a single project or set of activities, but on many complementary interventions. Managers cannot be held accountable for impact.
The step from the internal perspective to the external is often referred to as the ‘missing middle’ as it is not explicitly expressed in tools such as the logframe, yet it is the most important step in the results chain where people’s behaviour changes in response to outputs and thereby leads to progress towards outcomes.
Management control versus external factors
Show the third and last part of the slide
These diagrams illustrate the internal/external dimensions. As management control diminishes so the influence of factors that are external and outside management control become more important.
The risks of not achieving outcomes increase and those risks need to be taken into account during the planning process.

## Slide 4: How do you plan to measure it?
Are these set methods, and templates to ensure consistency in measurement?
Is there a system to store and collate data?
When do they measure it?
“The only man who behaves sensibly is my tailor; he takes my measurements every time he sees me, while all the rest go on with their old measurements and expect me to fit them”
George Bernard Shaw

## Slide 5: What is the Budget?
How much would the planned activities cost?
Cost efficiencies and cost minimisation
  How much can be done as part of routine reporting and management monitoring?
  What requires specific evidence gathering?
  What uses secondary data generated by others?
Notes: The key idea here is that this approach allows all of the meaningful and critical stages in a change process to be documented, rather than abstracted into just a few standardised elements in the log-frame

## Slide 6: Translate into a structured plan
Purpose and objectives of the plan. Systems for learning and responding. Who, What, When, How much