## Slide 1: Measuring your impact vs. activity

## Slide 2: Measuring change
Activity
Outcome
Impact
Output

## Slide 3: Impact Statement
The impact statement is a long-term objective that the project aims to contribute to but is outside of the timeframe of the proposed project
All DFID funded Darwin projects are expected to contribute to poverty reduction and sustainable management of biodiversity and its products
No indicators required by Darwin

## Slide 4: Outcome
The outcome statement is the overarching objective of the project you have outlined
Darwin projects are evaluated against their outcome statement
Indicators should provide detail of:
  What will change
  How it will change
  What you measure to define the change
And depending on the work
  Who will benefit

## Slide 5: Outcome indicators
Direct benefits
Household income in 500 HH increases by 10% (from $100 a month to $110 a month) by year 3
Wild stork numbers increase from 200 breeding pairs to 220 breeding pairs by year 3.
50 % people surveyed demonstrate increase in awareness of benefits of climate change adaptation
Indirect benefits
26,000 ha of natural forest gazetted for protection by year 3.
Increased capacity in Government agencies supporting biodiversity conservation as evidenced by an increase in EIAs meeting international best practice

## Slide 6: Output
Outputs are the specific, direct deliverables of the project.
These will provide the conditions necessary to achieve the Outcome. That is, if the outputs are achieved then the logic is that the outcome will also be achieved.
Output indicators should represent the direct deliverables of the project.
They should remain in the control of the project.
Darwin projects will need to report against their outputs annually

## Slide 7: Output indicators
Four community agroforestry pilot projects established, supported by technical research by year 3.
Fully functioning elasmobranch data collection programme established that is harmonised with regional IOTC reporting requirements.
Educational materials on benefits of conservation farming.

## Slide 8: Activity
What the general activities need to be undertaken in order to achieve the outputs and therefore the outcome of the project.
Activities should be designed in a way that their completion should be sufficient and indicators should not be necessary.
Darwin projects will not be evaluated against their activity.

## Slide 9: Example activities – not indicators
Documentation of lessons learned from implementation in each site/country
Conduct an exposure / cross visit for selected local staff and community members to project sites / communities that have HWC mitigation strategies in place.
Physical and hydrological assessment of Hilsha fishery

## Slide 10: Key points
Activity does not necessarily demonstrate impact
  i.e. 10 people trained does not necessarily show increased capacity to manage biodiversity
  i.e. distribution of funds to pilot projects does not show ventures are operating independently

## Slide 11: Key points cont.
Production of a deliverable does not necessarily demonstrate impact
  i.e. publication of a management plan does not necessarily show increased protection for biodiversity
  i.e. production of a taxonomic catalogue does not necessarily show it is being used to support biodiversity assessments

## Slide 12: Key Points cont.
Outcome indicators may not be measurable until the final year of a project
Output indicators should be measurable on a yearly basis
Activities are easy to discuss but should not be your only measure of progress